## Sheet1
Progress | Week | Monday | Goal
4.167% | 1 | 2018-09-03 | Fixed date for Verteidigung, drafted title and table of contents, set up writing environment, get in touch with Feng Cheng with initial plan and ask for support
8.333% | 2 | 2018-09-10 | Führung und Verantwortung Seminar Set up development environment and targets
12.5% | 3 | 2018-09-17 | Meet Haojin and receive pointers Set up initial TOC draft
16.67% | 4 | 2018-09-24
20.83% | 5 | 2018-10-01 | -- Urlaub --
25% | 6 | 2018-10-08 | -- Urlaub --
29.17% | 7 | 2018-10-15
33.33% | 8 | 2018-10-22
37.5% | 9 | 2018-10-29
41.67% | 10 | 2018-11-05
45.83% | 11 | 2018-11-12
50% | 12 | 2018-11-19
54.17% | 13 | 2018-11-26
58.33% | 14 | 2018-12-03
62.5% | 15 | 2018-12-10
66.67% | 16 | 2018-12-17
70.83% | 17 | 2018-12-24 | -- Urlaub --
75% | 18 | 2019-01-02 | Benchmark
79.17% | 19 | 2019-01-07 | Benchmark
83.33% | 20 | 2019-01-14 | First draft
87.5% | 21 | 2019-01-21 | Write
91.67% | 22 | 2019-01-28 | Write
95.83% | 23 | 2019-02-04 | Write
100% | 24 | 2019-02-11 | Write
Formulas:
Monday = [Monday, row above]+7